## Sheet1
Functionality | InsuranceType | Status | Comments
Schedule | Domestic | Dev-Done | Currently done like website, need to check with bkic it okay or not if the need change need to work on that
| Travel | Dev-Done | Currently done like website, need to check with bkic it okay or not if the need change need to work on that
| Home | Dev-Done | Currently done like website, need to check with bkic it okay or not if the need change need to work on that
| Motor | Dev-Done | Currently done like website, need to check with bkic it okay or not if the need change need to work on that
PolicySave/Authorize | Domestic | Done(TISCO/BBK) | Need to confirm the calculations(both Premium/Commision)
| Travel | Done(TISCO/BBK) | Need to confirm the calculations(both Premium/Commision)
| Home | Done(TISCO/BBK) | Need to confirm the calculations(both Premium/Commision)
| Motor | Done(TISCO/BBK) | Need to confirm the calculations(both Premium/Commision)
Ageny Add/Edit/Delete |  | Done | Our end tested.BKIC need to test.
Branch Add/Edit/Delete |  | Done | Our end tested.BKIC need to test.
Category Add/Edit/Delete |  | Done | Our end tested.BKIC need to test.
InsuredUser Add/Edit/Delete |  | Done | Our end tested.BKIC need to test.
AgencyUser Add/Edit/Delete |  | Done | Our end tested.BKIC need to test.
InsuranceProduct Add/Edit/Delete |  | Done | Our end tested.BKIC need to test.
Endoresement | Motor | Not Done | PageDesign(Done), Need Calcualtion from BKIC
| Home | Not Done | PageDesign(NotDone)Need Calcualtion from BKIC
HIRStatusWorkFlow | Motor | Not Done
| Home | Not Done
| Domestic | Not Done
| Travel | Not Done
Reports | Motor |  | Need to design and need inputs from BKIC
| Home |  | Need to design and need inputs from BKIC
| Domestic |  | Need to design and need inputs from BKIC
| Travel |  | Need to design and need inputs from BKIC
Dashboard | BKICADMIN | Not Done | Need Information from BKIC
| BRANCHADMIN | Not Done | Need Information from BKIC
Email Integration | Motor | Not Done
| Home | Not Done
| Domestic | Not Done
| Travel | Not Done
New-Policy Oracle Integration | Motor | Done | Tested with faheem in testOracleDB
| Home | Not Done | Faheem need to provide schema
| Domestic | Not Done | Faheem need to provide schema
| Travel | Done | Tested with faheem in testOracleDB
Renewal with Oracle Integration | Motor | Not Done | Need Information from BKIC
| Home | Not Done | Need Information from BKIC
| Domestic | Not Done | Need Information from BKIC
| Travel | Not Done | Need Information from BKIC